|  |
| --- |
| **PSL Foundation| PolicyEngine Policy Analysis Expansion** |
| **PCI’s North Star**: Every child is thriving and flourishing by age three. Every family has access to the resources and supports they need to help their children thrive.  **Impact Goals**:   * By 2027, 100% of families with children in the US live in states and communities in which significant new public resources have been invested in PN-3 supports. * By 2027, 100% of families with children PN-3 that live in historically underinvested communities in PCI-funded “system” states are connected to resources they want and need so their families can thrive and with significant progress towards this goal being made by PCI-funded “movement” states. |
| **Strategy:** Movement Building |
| **Grantee Impact Statement**: Provide cost and impact modeling of family economic security policies across all 50 states, leading to better informed decision making. |

| **Strategies** | **Indicators/Measures of Success** | **Completion Dates** |
| --- | --- | --- |
| A Child Poverty Impact Dashboard will be established showing child poverty rates by state and regions with ability to simulate federal and state tax and benefit policy changes. | Dashboard users will model Child Tax Credit (CTC), Earned Income Tax Credit (EITC), dependent exemption reforms, universal basic income (UBI), and SNAP with variations by amount, age eligibility (prenatal-3, 0-5, 0-17), earnings/income basis, marital status, phaseout thresholds and rates, plus state-specific levers and ability to introduce new state-level CTCs. | 2026-04-30 |
| Dashboard will display results showing fiscal cost, child poverty impacts (overall and ages 0-3), and distributional effects by income decile. | 2026-04-30 |
| Dashboard will incorporate prenatal to age three outcomes. | 2026-04-30 |
| Expand PolicyEngine's rules engine to model TANF and Child Care and Development Fund eligibility and benefit calculation rules in all 50 states. | Implement state-specific policy rules for all 50 states to enable complete nationwide policy analysis. Deliver programmatic representation of each state’s rules without microsimulation calibration. | 2026-10-31 |
| Provide expert consultation and training to support use of these resources at the national and state levels. | Provide training sessions and analytical support to national PN-3 partners including the Niskanen Center and the PN-3 Policy Impact Center. | 2026-10-31 |
| Conduct webinars on using PolicyEngine tools for child poverty analysis. Leaders in at least 30 states will participate in webinars and utilize the tools. | 2026-10-31 |